## Nov 8-12nd
Activity | Status (RAG) | Goals / Achievements | Time (days) | Risks | Comments
Postclick Access
GCP | A | Access | 5
VPN instaclick | G | Access | }
VPN Postclick | G | Access | 3
PoC updating
Markov chain as recommender system | G | Research of markov chain as recommendation system | 1
Recommender system Model | G | Understanding Hypothesis built (Markov Chain) | 1
Data Knowledge
Chekc distribution of the data | G | General understanding of the data train and test | 2
Chekc distribution of blocks over industry | G
Check distribution of number of blocks | G
Settle down modeling scope | G | Validate which path: - block_id or block(class) - Bussiness metrics | 1

## Nov 15-19th
Activity | Status (RAG) | Goals / Achievements | Time (days) | Risks | Comments
Postclick Access
GCP | G | Access | 5
Kibana | G | Access | 2
Markov process EDA
Check distribution of the transition matrix | G | Probabilites of blocks ids | 1.5
Check distribution of the block-ids given footer | G | Validate probabilites of blocks given footer
Check distribution of the footer given block-ids | G | Validate probabilites of footer given other blocks | 1.5
Check why is footer recommended at first places | G | Understanding what blocks provides the highest probabilities
Understand probablity distribution of API probabilities |  | Understanding why footer is being at first three places from API
Check distribution of the footer API probabilities |  | Validate probabilites of footer given other blocks API
Block recommeder stop |  |  |  |  | Se deja listo el analisis y la socializacion de las conclusiones con el cliente (Peter)
Validate hypothesis of correlation with length and types | G | Understand if there is a correlation between length and block ids | 1

## Nov 22-26th
Activity | Status (RAG) | Goals / Achievements | Time (days) | Risks | Comments
Markov process EDA
Gather API information |  | Get information | 1.5
Check distribution of the block-ids given footer API |  | Distribution of probabilities given footer | 0.5
Check distribution of the footer given block-ids API |  | Distribution of conditional probabilities goven other blocks | 0.5
Check why is footer recommended at first places API |  | Understanding probabilities that give footer in first three places | 0.5
Block recommeder stop
Understand conditional probability of types given industry |  | Understand if there is correlation between lenght and type | 0.5
Understand conditional probability of industry given lenght |  | Understand if there is correlation between lenght and industry | 0.5
Check distribution of types given industry and length |  | Understand relation between block types under industry and layout sizes | 1